Digital Egypt Pioneers Initiative (DEPI)

Graduation Project

Project Planning & Management

UK Train Rides – Power BI Data Analysis

Team Members

| Track | Member 1 | Member 2 |
| --- | --- | --- |
| Data Cleaning | Rwaa Ahmed | Mariam Mostafa |
| DAX & Measures | Ibrahim Haitham | Asmaa Mohamed |
| Dashboard | Omar Mostafa | Eman Nabil |

1. Project Overview

This project analyzes UK railway ticket sales and journey performance data using Microsoft Power BI. The dataset records individual ticket purchases together with journey details such as stations, times, ticket type, price, journey status (on time, delayed, cancelled), delay reasons, and refund requests.

The goal is to turn this raw transactional data into clear insights and an interactive dashboard that supports decision makers at a railway operator in understanding demand, revenue, and service reliability.

2. Objectives

- Clean and preprocess the raw dataset so it is ready for analysis.

- Define the analysis questions that decision makers would care about.

- Forecast the number of rides for the next month and the expected revenue for each day, including demand across ticket classes.

- Build an interactive Power BI dashboard that answers the analysis questions.

- Deliver a final report and presentation summarizing the work, findings, and recommendations.

3. Scope

- Data cleaning and transformation in Power BI (Power Query).

- Data modeling and DAX measures.

- Revenue and ride-count forecasting for the next month.

- Interactive dashboard design and delivery.

- Documentation: planning, literature review, requirements, final report, and presentation.

4. Team Structure and Roles

The team is divided into three tracks. Each track owns its deliverables, and all members contribute to the shared documents and the final presentation.

| Track | Members | Responsibilities |
| --- | --- | --- |
| Data Cleaning | Roaa Ahmed, Mariam Mostafa | Inspect the raw data, handle missing values and duplicates, fix data types, standardize categories, create derived columns (e.g., delay minutes), and document every cleaning step. |
| DAX & Measures | Ibrahim Haitham, Asmaa Mohamed | Build the data model and DAX measures (revenue, ride counts, delay and cancellation rates, refund rates), define analysis questions, and produce the forecasts. |
| Dashboard | Omar Mostafa, Eman Nabil | Design the dashboard layout, visuals, filters and slicers, and storytelling; test usability and prepare the dashboard documentation. |

Shared responsibilities: project documentation, GitHub repository maintenance, weekly team review, and the final report and presentation.

5. Project Timeline

The project runs over four weeks, following the structure required by the program.

| Week | Phase | Tasks | Owner |
| --- | --- | --- | --- |
| Week 1 | Data Cleaning & Preprocessing | Clean and preprocess the data in Power BI; produce the cleaned dataset and a preprocessing notebook/documentation. | Data Cleaning track |
| Week 2 | Analysis Questions | Define all possible analysis questions; forecast next month's rides and daily revenue; analyze demand by ticket class. | DAX & Measures track |
| Week 3 | Dashboard | Build the Power BI dashboard that visualizes the answers to the analysis questions. | Dashboard track |
| Week 4 | Final Presentation | Prepare the final report and presentation covering analysis, models, and results. | All members |

6. Deliverables

| Deliverable | Format | Responsible |
| --- | --- | --- |
| Project Planning & Management | Word (.docx) | All members |
| Literature Review | Word (.docx) | All members |
| Requirements Gathering | Word (.docx) | All members |
| Cleaned dataset + preprocessing documentation | Excel/CSV + document | Data Cleaning track |
| Analysis questions and DAX measures | Document + .pbix | DAX & Measures track |
| Power BI dashboard | .pbix + screenshots | Dashboard track |
| Final report and presentation | Word + PowerPoint | All members |

7. Tools and Technologies

| Tool | Purpose |
| --- | --- |
| Microsoft Power BI Desktop | Data cleaning (Power Query), modeling, DAX, and dashboard building. |
| Microsoft Excel | Initial data inspection and the data dictionary. |
| Microsoft Word / PowerPoint | Project documents, final report, and presentation. |
| Git & GitHub | Version control, collaboration, and project submission. |
| WhatsApp / Meetings | Team communication and weekly check-ins. |

8. Risk Management

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Poor data quality (missing values, inconsistent formats) | High | Early data profiling in Week 1; document assumptions for every correction. |
| Delays between tracks (dashboard depends on cleaning and DAX) | High | Agree on the cleaned data structure and measure names early; share intermediate files. |
| Forecasting accuracy limited by data volume | Medium | Use simple, explainable forecasting methods and state limitations clearly. |
| Merge conflicts or lost files | Medium | Use GitHub with a clear folder structure and one branch per member. |
| Large file sizes (.pbix, dataset) | Low | Share large files through cloud storage and link them in the README. |
| Team member unavailability | Medium | Pair members within each track so work can be covered. |

9. Communication and Version Control

- Weekly team meeting to review progress and plan the next steps.

- Shared GitHub repository containing data, documents, DAX, dashboard, and presentation folders.

- Each member works on a separate branch and submits changes through pull requests.

- Meaningful commit messages describing each change.

10. Success Criteria

- All required deliverables are submitted on time.

- The cleaned dataset has no unresolved missing values, duplicates, or wrong data types.

- The dashboard answers every defined analysis question and is easy to use.

- Forecasts for next month's rides and daily revenue are produced and explained.

- The final presentation clearly communicates insights and recommendations.